## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Sales project | Ghalia Saleh | 2020-06-28 | 2020-07-02 |  | 66% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 | manager features | Ghalia .S |  | 2022-06-28 | 2022-09-13 | 10 | Complete
| Feature 1 | General understanding of the system and its requirements | Ghalia .S |  | 2022-06-28 | 2022-07-01 | 4 | Complete
| Feature 2 | priority order requirements | Ali .m |  | 2022-07-01 | 2022-07-04 | 5 | Complete
| Feature 3 | stand on non-career requirement | Ghalia .S |  | 2022-07-04 | 2022-07-07 | 4 | Overdue | the need for alonger period !
| Sprint 2 | security features | Ali .m |  | 2022-07-07 | 2022-07-14 | 8 | In Progress
| Feature 4 | creat the means of communication | Ali .m |  | 2022-07-07 | 2022-07-08 | 1 | In Progress
| Feature 5 | follow up on customer requirements | Dina .a |  | 2022-07-08 | 2022-07-11 | 4 | Not Started
| Feature 6 | Achieving non-functional requirements | Ali .m |  | 2022-07-11 | 2022-07-14 | 4 | Not Started
| Sprint 3 | design features | Dina .a |  | 2022-07-14 | 2022-07-24 | 10 | Not Started
| Feature 7 | Statistics of the work of the system on the ground | Dina .a |  | 2022-07-14 | 2022-07-17 | 4 | Not Started
| Feature 8 | collect user reviews | Dina .a |  | 2022-07-17 | 2022-07-20 | 3 | Not Started
| Feature 9 | summarizing the work of the system | Ghalia .S |  | 2022-07-20 | 2022-07-24 | 3 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.